## Blad1
Project BarrocIT
Groep 4: obesicode
Groepslid: Noël van Bijnen
Datum |  |  | Tijd | Plaats | Verrichte werkzaamheden | Afspraken en opmerkingen
| Week 1 | ma | 9:00-12:15 |  | samenwerkingscontract gemaakt | Iedereen heeft tijd besteed aan met het gebruiken van Github.
| Week 1 |  |  |  | bereikbaarheidslijst gemaakt
| Week 1 | di | 9:00-12:15 |  | logboeken klaargezet
Week 1
| Week 1 | wo | 9:00-12:15 |  | keuzedeel
Week 1
| Week 1 | do | 9:00-12:15 |  | interviews gemaakt.
| Week 1 |  |  |  | pva aangemaakt voor verdere.
| Week 1 |  |  |  | vergadering
| Week 1 | vr | 9:00-12:15 |  | moscow aangemaakt voor verdere.
Week 1
| Week 2 | ma | 9:00-12:15 |  | moscow gewerkt
| Week 2 |  |  |  | beginnen uml use case
| Week 2 | di | 9:00-12:15 |  | moscow / pve tabel vorm gegeven
| Week 2 |  |  |  | uml's gewerkt
| Week 2 | wo | 9:00-12:15 |  | keuzedeel
Week 2
| Week 2 | do | 9:00-12:15 |  | uml usecase diagrammen en template af , tekeningen/prototypes
| Week 2 |  |  |  | vergadering
| Week 2 | vr | 9:00-12:15 |  | ziek
Week 2
| Week 3 | ma |  |  | ziek
Week 3
| Week 3 | di
Week 3
| Week 3 | wo |  |  | keuzedeel
Week 3
| Week 3 | do |  |  | sequentiediagrammen gemaakt
| Week 3 |  |  |  | vergadering
| Week 3 | vr
Week 3
| Week 4 | ma |  |  | moodboard website gemaakt
Week 4
| Week 4 | di
Week 4
| Week 4 | wo
Week 4
| Week 4 | do
Week 4
| Week 4 | vr
Week 4
| Week 5 | ma
Week 5
| Week 5 | di
Week 5
| Week 5 | wo
Week 5
| Week 5 | do
Week 5
| Week 5 | vr
Week 5